## Exemplar
Project Plant Pals: Hiring Day Communication Plan
Recipients | Type of Communication | Frequency | Sender/Owner | Key Dates | Delivery Method | Goal | Resource Links | Notes
Core Team | Daily Stand-Up | Daily | Project Manager | Monday-Friday at 3pm | In Person | Project planning and task updates to make sure the team stays on track
Facilities | Planning Meeting | Weekly | Core Team: Administrative Coordinator | Tuesdays at 2pm | Phone Call | Reserve rooms/spaces
Print Shop | Planning Check-In | Weekly | Core Team: Administrative Coordinator | Thursdays, including the day before the event | Phone Call | Coordinate printed materials/signage
Volunteers | Planning Check-In | Weekly | Core Team: Training Manager | Wednesdays, including a day-of-training reminder | Email (from individual address) | Coordinate with volunteers and send reminders
HR | Planning Meeting | Daily | Core Team: HR Specialist | Monday-Friday at 10am | In Person | Check in on planning progress, provide support to department
Your Manager | Project Update | Weekly | Project Manager | Monday afternoons | In Person | Update on event planning, ask questions, and get feedback
Candidates | Informational Update | Weekly | Core Team: HR Specialist | Fridays and the day before the event (Thursday) | Email (from company address) | Communicate schedule, location, and other necessary event details
Volunteers | Training | One time | Core Team: Training Manager | The Wednesday before the event | In Person | Train volunteers to check-in and welcome candidates and direct the flow of traffic during the event
Catering | Planning Check-In | Weekly | Core Team: Administrative Coordinator | Thursdays, including the day before the event | Phone Call | Coordinate coffee service/snacks for candidates and lunch for HR
Senior Leaders: Director of Operations and the Director of Product (CC your manager) | Project Update | One time | Project Manager | Debrief after the event | Email (from individual address) | High-level information and general updates

## Comm Plan Template 2 (hidden)
Project Communication Plan
Project Title:
Project Manager:
Executive Sponsor:
Principal Stakeholder:
Date:
Deliverable Info (What) | Recipient(s) (Who) | Delivery Method(s) (How) | Schedule (When) | Who's Responsible? (Owner)
Project Information
Project Status
Agenda Minutes
Timeline Update
Project Updates Action Item Status
Project Risks

## Comm Plan Template 3 (hidden)
| Purpose | Medium | Frequency | Audience
Kickoff meeting
Project team meetings
Check-ins/ meeting recap
Project status meetings
UX design reviews