## Tasks and Timeline
Sauce & Spoon Project Plan
Milestone | Task | Notes | Start Date | Due Date | Duration | Task Owner | Status | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[8 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[8 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
Determine the point-of-sale or POS software and the tablet supplier | Researching tablet features, comparing tablet pricing, and confirming compatible operating systems |  |  |  | 2
| Develop a Non-Disclosure Agreement (NDA) for procurement of the POS software and tablet vendor |  |  |  | 0.5
| Develop a Request For Proposal (RFP) with detial requirement on POS software and tablet vendor |  |  |  | 3
| Generate quotes and review costs by collecting Statement Of Works (SOWs) |  |  |  | 15
| Determine and sign contract with the menu tablet supplier. |  |  |  | 3
Develop photo achive of the menu items | finalized menu, coupon value mock-ups, and photoshoot the menu item | Meeting: Menu and Coupons, Meeting: Menu and Coupons |  |  | 0
| Design branding online menu |  |  |  | 3
| and store in a online gallery achive |  |  |  | 0
| Connect the online gallery achive to the POS system |  |  |  | 2
| Run out the testing on POS system |  |  |  | 0.5
Integrated the new POS software with the existing host software | Connect the POS software to the existing host software |  |  |  | 2
| Add menu updating feature to POS software by monitoring the host software |  |  |  | 4
| Add feature of post-dining survey for customer satisfication review |  |  |  | 4
| Add new analysis interface with metric tracking |  |  |  | 4
| Test out the compatibility of the integration and troubleshooting |  |  |  | 4
Installation of the tablet on the bar section. | determine the number of tablet and order for shipment | Meeting: Tablet Shipping Estimate |  |  | 0
| Get an electrician in the dinner section | Meeting: Project Update |  |  | 3
| Install tablets in the bar areas at the Downtown and North restaurant locations and and connect to the WiFi | Meeting: Project Update |  |  | 2
| Install/upgrade the integrated POS software on the tablet | Meeting: Scheduling Software Installation |  |  | 0
| Run out an internal testing and troubleshooting |  |  |  | 1
| swap out the old tablet with the new model | Meeting: Tablet Shipment Updates |  |  | 20
Train staff on the new system | Develop a training plan including preparations and planning | Meeting: Project Update |  |  | 7
| Pre-training meeting to introduce tablets and changes to staff before training them on the tablets, review the tipping and pay during the rollout of tablet pilot | Week 2 - Meeting: Project Update: 1 hour at each location |  |  | 1
| Seydou will train managers first | Week 2 - Meeting: Project Update: 2 hours |  |  | 1
| then managers will train all the staff at each location | Week 2 - Meeting: Project Update: 2 hours each training plus one hour before and after each training for facilitator prep/debrief |  |  | 5
| Invite family and friend to test run the tablet. |  |  |  | 3
Hiring | Determine and hire more employee |  |  |  | 20

## Task Brainstorm
Task Brainstorm
Milestone | Task | Notes | Estimated Duration (Days) | Optimistic | Most Likely | Pessimistic | Confidence Rating (H/M/L) | Known Dates
Determine the point-of-sale or POS software and the tablet supplier | Researching tablet features, comparing tablet pricing, and confirming compatible operating systems |  | 2 |  |  |  | M
| Develop a Non-Disclosure Agreement (NDA) for procurement of the POS software and tablet vendor |  | 0.5 |  |  |  | H
| Develop a Request For Proposal (RFP) with detial requirement on POS software and tablet vendor |  | 3 |  |  |  | H
| Generate quotes and review costs by collecting Statement Of Works (SOWs) |  | 15 |  |  |  | H
| Determine and sign contract with the menu tablet supplier. |  | 3 |  |  |  | M
Develop photo achive of the menu items | finalized menu, coupon value mock-ups, and photoshoot the menu item | Meeting: Menu and Coupons, Meeting: Menu and Coupons | 10 | 7 | 7 | 14 | L
| Design branding online menu |  | 3 |  |  |  | H
| and store in a online gallery achive |  | 1 | 0.2 | 0.4 | 1 | H
| Connect the online gallery achive to the POS system |  | 2 |  |  |  | H
| Run out the testing on POS system |  | 0.5 |  |  |  | M
Integrated the new POS software with the existing host software | Connect the POS software to the existing host software |  | 2 |  |  |  | H
| Add menu updating feature to POS software by monitoring the host software |  | 4 |  |  |  | M
| Add feature of post-dining survey for customer satisfication review |  | 4 |  |  |  | M
| Add new analysis interface with metric tracking |  | 4 |  |  |  | M
| Test out the compatibility of the integration and troubleshooting |  | 4 |  |  |  | M
Installation of the tablet on the bar section. | determine the number of tablet and order for shipment | Meeting: Tablet Shipping Estimate | 13 | 11 | 11 | 15 | H
| Get an electrician in the dinner section | Meeting: Project Update | 3 |  |  |  | M
| Install tablets in the bar areas at the Downtown and North restaurant locations and and connect to the WiFi | Meeting: Project Update | 2 |  |  |  | M
| Install/upgrade the integrated POS software on the tablet | Meeting: Scheduling Software Installation | 3 | 0.5 | 2 | 4 | L
| Run out an internal testing and troubleshooting |  | 1 |  |  |  | H
| swap out the old tablet with the new model | Meeting: Tablet Shipment Updates | 20 |  |  |  | H
Train staff on the new system | Develop a training plan including preparations and planning | Meeting: Project Update | 7 |  |  |  | H
| Pre-training meeting to introduce tablets and changes to staff before training them on the tablets, review the tipping and pay during the rollout of tablet pilot | Week 2 - Meeting: Project Update: 1 hour at each location | 1 |  |  |  | H
| Seydou will train managers first | Week 2 - Meeting: Project Update: 2 hours | 1 |  |  |  | H
| then managers will train all the staff at each location | Week 2 - Meeting: Project Update: 2 hours each training plus one hour before and after each training for facilitator prep/debrief | 5 |  |  |  | H
| Invite family and friend to test run the tablet. |  | 3 |  |  |  | H
Hiring | Determine and hire more employee |  | 20 |  |  |  | L

## Additional Resources
Additional Resources
Title | Date Added | Notes | Link
Restaurant Tablets- Is It Worth the Investment? | 2021-05-26 | 3 Things to Consider Before Investing in Restaurant Tablets: Enhancing Customer Experience, POS Integration, Upgrade Options. 6 Ways Tablets Can Transform the Dining Experience: Inclusivity, Personalization, Updated Menus, Minimized Wait Times, Reduced Human Error , Streamlined Orders | https://plumpos.com/restaurant-technology/restaurant-tablets.html
3 reasons why a tablet ordering system will ruin your restaurant | 2021-05-26 | Cost, Damaging the Brand Experience, Unpredictability | https://missdetails.com/3-reasons-why-a-tablet-ordering-system-will-ruin-your-restaurant/

## Quality and Evaluation
Quality and Evaluation
Quality Standards | Quality Standards
Category | Criteria/Description | Evaluation Questions | Evaluation Indicators | Criteria Met?
Productivity | 8 minutes of average ticket time for appetizers |  | average ticket time | FALSE
| 12-15 minutes of average ticket time for entrees |  | average ticket time | FALSE
Effectiveness | <1 minutes checkout time | Were there unintended outcomes? | checkout time | FALSE
| <10 minutes wait time |  | wait time | FALSE
| An 30 minutes average table turn time | Who is benefiting? | average table turn time | FALSE
| 5% more birthday celebrations across restaurant locations |  | number of birthday celebrations | FALSE
Functionality | less than 5% average rate of technical issues reported by customer | What is working and what’s not working? | technical issues reported by customer | FALSE
| 100% order accuracy |  | order accuracy | FALSE
Ease of use | under 30% asking for help using the app | Should we continue? | number of asking for help of using the app, total order number | FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## Survey Questions
Survey Questions
Quality Standards |  |  |  |  | Question Answer Options (depends on question type)
Criteria/Description | Evaluation Questions | Evaluation Indicators | Survey Question | Question Type | Option #1 | Option #2 | Option #3 | Option #4 | Option #5
8 minutes of average ticket time for appetizers |  | average ticket time | do you feel about the waiting time for your appetizer too long? | Yes/No | Yes | No
12-15 minutes of average ticket time for entrees |  | average ticket time | do you feel about the waiting time for your entrees too long? | Yes/No | Yes | No
<1 minutes checkout time | Were there unintended outcomes? | checkout time | rate how you satisfy with the checkout time | Scaled | 1 being needs improvement | 2 | 3 | 4 | 5 being excellent
<10 minutes wait time |  | wait time | According to the busy level when you arrivie, How long did you have to wait for a table? | Multiple choice | <5 mins | 5-8 mins | 9-12 mins | > 12 min | 5 being excellent
An 30 minutes average table turn time | Who is benefiting? | average table turn time | what is tht table turn time | Multiple choice | <15 mins | 15-20 mins | 20-25 mins | 25-30 mins | >30 mins
5% more birthday celebrations across restaurant locations |  | number of birthday celebrations | How do you use the tablet during the dinnner experience? | Open-ended
less than 5% average rate of technical issues reported by customer | What is working and what’s not working? | technical issues reported by customer | How difficult you find to using the tablet to find your order | Scaled | 1 being needs improvement | 2 | 3 | 4 | 5 being excellent
100% order accuracy |  | order accuracy | Does the order accurate? | True/False | TRUE | FALSE
under 30% asking for help using the app | Should we continue? | number of asking for help of using the app, total order number | Rate overall experience was like | Scaled | 1 being needs improvement | 2 | 3 | 4 | 5 being excellent