## Retrospective Ideas
Feedback From: | Type: | Description: | Evidence: | Actions:
Project team | Went well | got all the tablets installed and working at my location. all the guests got the hang of the tablets and payments worked for the most part
Project team | Went well | Tickets came through at a good pace and were easy to keep track
Project team | Needs improvement | The food came out on time, but table turn time stayed about the same. | 14% people take 30+ mins to receive your food order
Customers | Needs improvement | Some orders got sent back | 28% orders were prepared incorrectly | implementing some updates to kitchen operations
Customers | Needs improvement | we discovered a few technical issues during the POS integration process | 12% people had technical issues with tablet | we were able to quickly address them and get them fixed
Project team | Needs improvement | There will be routine maintenance issues that pop up, it just comes with the territory. They are managed by identify what type of issue. |  | Update the process manual to easily find next time that issue comes up
Customers | Went well | we met most of our customer satisfaction standards. | Only 4% people said laking experience with the tablet overall.
Customers | Needs improvement | didn’t get many participants for the birthday club | 84% people did not sign up for the Birthday Club | proactively working to grow the participant list. working with the designer to update the content on the website and the tablets so it’s clearer what the program is
Project team | Needs improvement | a few internal operational issues that we didn’t plan for and that impacted the team’s ability to carry out tasks smoothly |  | understanding each location’s history before planning gets underway
Project team | Needs improvement | tablet implementation took just a little bit longer than we hoped |  | making sure things are properly planned based on everyone’s availability.
Project team | Needs improvement | lack of understanding between what the front of house staff does and the back of house staff does. |  | Scale up the back of the house before the front of the house so that they’re fully prepared for changes and influx. Share experiences to help each end work together in a more harmonious way. Removes the tendency to blame one another if issues come up
Project team | Needs improvement | lack of understanding between what the front of house staff does and the back of house staff does. |  | Develop a more comprehensive training session, even break it up into two parts. Address other aspects of daily service operations in addition to how to use the tablets